## Slide 1
hūmānus
year-to-date update · Q2 2026 Board Meeting
29 June 2026
Humanising Justice
ACCOUNTABILITY · COMMUNITY · EVIDENCE
Sponsor: Eva Buzo, Executive Director · Agenda item 4 · 15 minutes · Discussion

## Slide 2
Three goals guide everything we do
Our 2024–29 strategy frames the year.
1
Victims secure outcomes in line with their own conception of justice.
2
Victims are empowered by the process of pursuing justice — not just by its results.
3
Justice processes are transformed to put victims at the centre.
2026 is the first full year operating as hūmānus (stichting) under the new statutory structure.
hūmānus · Q2 2026 Board Meeting · Operations & Impact Update
2 / 10

## Slide 3
Where the work has sat this year
Y2D 2026 (January–May) by funded programme and other significant strands.
Programme / strand
Funder
Y2D status
Towards a More Peaceful Arakan
Swiss FDFA via Stimson Center
Live — partnership signed Feb 2026; active from Dec 2025; runs to May 2027.
Bangladesh dialogue
FCDO (UK)
Continuing dialogue programme; Asia trip with Stimson reviewed Q1.
OSF South Asia — Rohingya in India
Open Society Foundations
$300k received Jan 2026; India litigation, RSU partnership, HDCO/Bridging Changes consultation in flight.
Women's Dialogue
SDC (under VAI legacy entity)
Grant close-out — ends 30 April 2026; 3rd narrative + finance reports due May.
Adani / UniSuper / APRA
Self-directed (no external grant)
New strand from March 2026; substantial volume.
Meta Inc. accountability
Self-directed
Civil proceedings in Ireland continuing; SEC pathway live.
Detail on each strand follows. Finance picture: see Reserves Prognosis (paper 04) and YTD Grant Spend (paper 05).
hūmānus · Q2 2026 Board Meeting · Operations & Impact Update
3 / 10

## Slide 4
Towards a More Peaceful Arakan
Swiss FDFA, via Stimson Center as prime · hūmānus as implementing partner
What the project is
An 18-month partnership to identify, create, and support trust-building opportunities among Rohingya, Arakanese, and Bangladesh stakeholders, against the backdrop of the Arakan Army's consolidation across northern Arakan. The project combines bilateral engagement, capacity building, and facilitated dialogue — and gives hūmānus a structured channel into Track-2 work on the Bangladesh–Myanmar border.
Where we are
Partnership agreement signed 5 February 2026, effective from 1 December 2025, runs to 31 May 2027.
Y2D: workplan kicking off; bi-weekly check-in cadence with Stimson; Q1 Asia trip with Stimson reviewed against the Bangladesh political transition.
Programmatic focus reflected in the 2025 dialogue model — sustained weekly engagement with Rohingya leadership and inter-ethnic dialogue with Rakhine and Bangladeshi counterparts.
hūmānus · Q2 2026 Board Meeting · Operations & Impact Update
4 / 10

## Slide 5
Bangladesh dialogue programme
FCDO (UK) · continuing programme
What the funding supports
Sustained dialogue and engagement work with Rohingya leadership in Bangladesh, complementing the Swiss/Stimson Arakan partnership. Operates in a deficit / reimbursement model — hūmānus spends and is reimbursed in arrears, which is why cash-flow management is a standing board item.
Where we are
Continuing engagement through Q1; programme management transitioned to Shafi following Jaya's departure.
Asia trip with Stimson reviewed Q1 against the Bangladesh political situation; status to be confirmed at the meeting.
Cash-flow discipline: deficit-model reimbursement remains a watch-item — addressed in papers 04 and 05.
hūmānus · Q2 2026 Board Meeting · Operations & Impact Update
5 / 10

## Slide 6
OSF South Asia — Rohingya in India
Open Society Foundations · USD 300,000 grant received January 2026
What the grant supports
Strategic work on Rohingya in India: protecting detained refugees through legal intervention, building a cross-state network of lawyers, and feeding evidence and analysis into wider Rohingya advocacy.
Y2D streams
India detention database — partnership with the Azadi Project; live and in active use.
Litigation strand — habeas corpus drafting and bail applications under way since January; RTI / petitioner-search work continuing; lawyer outreach in J&K; quarterly report of developments commissioned end-March.
Rohingya Student Union — stakeholder analysis partnership; formal kick-off and work-plan location to be confirmed at the meeting.
Bridging Changes Coalition / HDCO — Rohingya-in-India closed-door consultation in flight (scoped Q1); date and outputs to be confirmed at the meeting.
hūmānus · Q2 2026 Board Meeting · Operations & Impact Update
6 / 10

## Slide 7
Women's Dialogue — grant close-out
SDC (Swiss) · contracted under VAI legacy entity · grant ends 30 April 2026
Where the work has sat in 2026
Y2D activity has been close-out, not new convenings — spending plan for the remainder of the grant, plus the 3rd narrative report and 3rd finance report (due 15 May 2026).
Grant terminated 30 April 2026; final reporting and reconciliation in train.
Project sits under the VAI legal entity. Audit report in this pack is VAI 2024 (paper 06) — implications for donor-renewal positioning are touched on under strategic outlook.
Why this matters for the Board
Closing out an SDC grant under VAI while building a Swiss FDFA relationship under hūmānus (via Stimson) — this is the entity transition playing out across two live Swiss-funded workstreams. Worth attention on continuity of relationships in Bern and Dhaka.
hūmānus · Q2 2026 Board Meeting · Operations & Impact Update
7 / 10

## Slide 8
Other significant work
Not externally project-funded, or peripheral to the funded portfolio.
Adani / UniSuper / APRA strand
New and active workstream from March 2026. Includes APRA complaint work (Cbus deep-dive), Adani Investors briefings (Australian fiduciary case law, super-fund exposure to Adani / GQG), Adani Defence scoping, OFAC Iran civil-probe briefing, and a UniSuper PHD review. Substantial volume — Board may wish to take a dedicated update at a future meeting.
Meta Inc. accountability & Mohib Ullah
Civil proceedings in Ireland continuing on behalf of sixteen plaintiffs; SEC pathway active. Mohib Ullah submission to the UN Special Rapporteur progressed (Hashmat feedback Q1).
Comms and external engagement
Pitch notes drafted (April) for Rebecca Henschke (BBC World Service / BBC Eye) and Kristen Gelineau (AP). Foreign Correspondents-style convening late May with Aditi and Nazia. Geneva convening mid-May.
Governance — Els onboarding
Statutory director onboarding workstream completed April 2026: contracts, notary documents and statutes update, insurance cover with Els's broker. Closes Q1 action 9.
hūmānus · Q2 2026 Board Meeting · Operations & Impact Update
8 / 10

## Slide 9
Strategic outlook and watch-items
Things to keep in view between now and the Q3 meeting.
Reserves and deficit-model donors
FCDO and Swiss reimburse in arrears; cash-flow discipline remains critical. Detail in papers 04 (Reserves Prognosis) and 05 (Y2D Grant Spend).
VAI ↔ hūmānus entity transition
Two active Swiss-funded workstreams straddle the transition — SDC Women's Dialogue closing out under VAI; Swiss/Stimson Arakan running under hūmānus.
Bangladesh operating environment
Political situation under the new government continues to shape Bangladesh dialogue and Stimson partnership delivery.
Beyond 2029 / post-OSF horizon
Picked up under agenda item 6 (strategic discussion) — matching ambition to a minimal-fundraising posture.
Hiring posture
Eva remains cautious on new permanent hires in the short term following Q1 reflection; no new joiners Feb–May 2026.
hūmānus · Q2 2026 Board Meeting · Operations & Impact Update
9 / 10

## Slide 10
hūmānus
Humanising justice
ACCOUNTABILITY · COMMUNITY · EVIDENCE
www.humanus.co · hello@humanus.co
Q2 2026 Board Meeting · Operations & Impact Update · Sponsor: Eva Buzo (ED)