Forecast Report — October 2026 to June 2027

2026 full-year outturn and nine-month cash forecast

Board meeting  29 October 2026 (virtual)

Opening position  Xero 30 September 2026; cash checked live 12 October 2026

Prepared by  Stacy McGill, Finance Manager

Currency  USD; GBP and EUR converted at Xero rates of late Sep / early Oct 2026

Companion paper  Board Finance Report, Q3 2026

1. Headline

The 2026 deficit comes from income timing and SDC co-funding, not overspending. Core (OSF) activity runs a surplus of about USD 30,431. Even so, cash runs short twice before the OSF Year-3 tranche arrives in January 2027: at the 28 October payment run, and in December.

2026 outturn (central): expenditure USD 509,568, which is 4.3% over the working budget (USD 488,450) and 19% under the board-approved budget (USD 631,450). Income USD 468,581. Reported deficit USD 40,987.

What drives the deficit: SDC co-funding USD 45,660; grant income earned in 2026 but claimable only in 2027, USD 33,614. These are partly offset by the core surplus.

Cash, central case: USD (6,101) at end-October, USD 13,202 at end-November (after the FCDO claim), USD (21,230) at end-December, then USD 269,219 at end-January once OSF pays.

Even with a complete spending freeze, cash is short: USD (1,101) in October and USD (6,230) in December. Cutting costs alone cannot fix this; the receipts have to come earlier.

What fixes it: OSF releasing the January tranche in December (it paid in December in 2024) or Stimson paying the FCDO claim on receipt and Swiss tranche 2 in December, together with a freeze on discretionary spending.

Decisions needed (D2–D4 in the Board Finance Report) Freeze discretionary spending (travel, meetings, partner grants, new consultancy) until the OSF tranche is received. FCDO-reimbursable activity is exempt. Authorise the ED to ask OSF in writing to release the Year-3 tranche in early December 2026, and to ask Stimson to pay FCDO claim 1 on receipt and Swiss Myanmar tranche 2 in December. Agree a payment order for the 28 October run if the shortfall is not covered by then. Proposed: the Chair's stipend and other non-staff bills are deferred to November. Mandate the ED and Chair to arrange a standby bridge of up to USD 75,000 (enough to cover the FCDO claim slipping to January). Use it only if neither OSF nor Stimson confirms by 20 November.

2. 2026 full-year outturn

Accrual basis, central case. Q4 is built from committed costs (repeating invoice templates, approved bills, the Communications Advisor's monthly invoice) plus USD 5,000 a month of programme and travel spending.

| USD | Actual YTD (9 mo) | Forecast Q4 | Forecast FY 2026 | Working budget | Board budget |
| --- | --- | --- | --- | --- | --- |
| Income | 415,681 | 52,900 | 468,581 | 488,450† | 631,450† |
| Expenditure | 401,897 | 107,671 | 509,568 | 488,450 | 631,450 |
| Net surplus / (deficit) | 13,783 | (54,771) | (40,987) | – | – |
| Net assets at year-end (Xero basis) |  |  | (17,194) |  |  |
| Add: earned grant income to accrue (FCDO II Nov–Dec, Swiss Myanmar) |  |  | 33,614 |  |  |
| Adjusted net assets at 31 Dec 2026 |  |  | 16,420 |  |  |

† Both budgets were set as balanced plans: the funding columns equal planned spend. Income includes FCDO Phase II claim 1 (Jun–Oct, about USD 52,800) on the basis that it is invoiced in October.

Where the deficit comes from

| Driver | USD |
| --- | --- |
| SDC final-year co-funding (Art. 1.2 — FDFA covers max 50%) | (45,660) |
| Restricted timing — spent in 2026, claimable in 2027 (FCDO II Nov–Dec + Swiss Myanmar) | (33,614) |
| FCDO Phase I — 2026 receipts covering 2025 spend | 8,133 |
| FCDO Phase II Jun–Oct — claim matched to spend | – |
| Core (OSF #4 + interest) — income less core spend | 30,431 |
| FX revaluation and legacy codes | (277) |
| Reported 2026 deficit (central) | (40,987) |

SDC co-funding is a one-off. SDC closed on 30 April and is fully drawn, so this does not recur in 2027.

The timing items reverse in 2027. FCDO Phase II Nov–Dec costs are claimed in the April 2027 report, and the Swiss Myanmar costs are covered by tranches 2 and 3.

Core is in surplus. OSF-funded spending of about USD 271,268 is below the USD 286,635 working-budget allocation and inside the USD 300,000 tranche.

Expenditure by budget line — full-year forecast

| Budget line | Working budget | Board budget | Actual YTD | Forecast FY | FY vs working |
| --- | --- | --- | --- | --- | --- |
| Executive Director | 170,400 | 170,400 | 127,800 | 170,400 | – |
| COLA | 21,600 | 21,600 | 16,931 | 22,499 | 899 |
| Senior Legal Advisor | – | 120,000 | – | – | – |
| Programme Manager | 42,000 | 42,000 | 34,000 | 44,500 | 2,500 |
| Project Manager (Rohingya Manager) | 31,250 | 31,250 | 22,500 | 30,000 | (1,250) |
| Communications Advisor | 64,800 | 64,800 | 48,462 | 64,612 | (188) |
| Communication Support | 14,400 | 14,400 | 11,867 | 13,815 | (585) |
| Finance Manager | 24,000 | 24,000 | 18,000 | 22,000 | (2,000) |
| Operations Support | 18,000 | 18,000 | 6,267 | 7,195 | (10,805) |
| Vehicle Hire & Sundry | 6,000 | 6,000 | 2,286 | 2,886 | (3,114) |
| Volunteer Stipends | 12,000 | 12,000 | 12,334 | 12,334 | 334 |
| Partner Expenses (Azadi) | 30,000 | 30,000 | 14,000 | 18,000 | (12,000) |
| Lawyer Fees | 12,000 | 24,000 | 4,363 | 4,363 | (7,637) |
| Audit | 3,000 | 3,000 | 2,822 | 2,822 | (178) |
| Board Meetings | 4,000 | 4,000 | 8,936 | 8,936 | 4,936 |
| Technology & Software | 5,000 | 5,000 | 5,469 | 6,527 | 1,527 |
| Travel Expenses | 25,000 | 36,000 | 39,178 | 47,578 | 22,578 |
| Fees (bank) | 5,000 | 5,000 | 511 | 678 | (4,322) |
| Unbudgeted — Confidence Building Measures (FCDO I funded) | – | – | 14,598 | 14,598 | 14,598 |
| Unbudgeted — Meeting Expenses | – | – | 8,930 | 10,930 | 10,930 |
| Unbudgeted — Project Consultants | – | – | 2,294 | 4,545 | 4,545 |
| Unbudgeted — Depreciation | – | – | 114 | 114 | 114 |
| FX revaluation | – | – | 235 | 235 | 235 |
| Total | 488,450 | 631,450 | 401,897 | 509,568 | 21,118 |

3. Cash forecast — October 2026 to June 2027

Month-end closing cash, USD. Central case below. Every column is one month of cash in and cash out.

| USD | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Opening cash | 33,679 | (6,101) | 13,202 | (21,230) | 269,219 | 234,722 | 200,225 | 162,728 | 175,230 |
| Executive Director | 14,200 | 14,200 | 14,200 | 14,200 | 14,200 | 14,200 | 14,200 | 14,200 | 14,200 |
| Communication Advisor | 5,383 | 5,383 | 5,383 | 5,383 | 5,383 | 5,383 | 5,383 | 5,383 | 5,383 |
| Advocate / Programme Manager | 3,500 | 3,500 | 3,500 | 3,500 | 3,500 | 3,500 | 3,500 | 3,500 | 3,500 |
| Rohingya Manager (cash) | 1,500 | 1,500 | 2,435 | 2,500 | 2,500 | 2,500 | 2,500 | 2,500 | – |
| Cost of Living Allowance (GBP 1,400) | 1,856 | 1,856 | 1,856 | 1,856 | 1,856 | 1,856 | 1,856 | 1,856 | 1,856 |
| Finance Manager (SK Das) | 2,000 | 1,000 | 1,000 | 1,000 | 1,000 | 1,000 | 1,000 | 1,000 | 1,000 |
| Communication Support | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 | 649 |
| IT & software | 353 | 353 | 353 | 353 | 353 | 353 | 353 | 353 | 353 |
| Bank charges | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 |
| One-off committed bills | 5,283 | – | – | – | – | – | 3,000 | – | – |
| Programme & travel (central) | 5,000 | 5,000 | 5,000 | 5,000 | 5,000 | 5,000 | 5,000 | 5,000 | 5,000 |
| Total cash out | 39,780 | 33,497 | 34,432 | 34,497 | 34,497 | 34,497 | 37,497 | 34,497 | 31,997 |
| FCDO Phase II claim Jun–Oct 2026 (Schedule 2, ind. Nov 2026) | – | 52,800 | – | – | – | – | – | – | – |
| OSF #4 Year-3 tranche (contract: January 2027) | – | – | – | 300,000 | – | – | – | – | – |
| Swiss Myanmar tranche 2 (§3.3: 31 Jan 2027) | – | – | – | 24,947 | – | – | – | – | – |
| FCDO Phase II final claim Nov 26–Mar 27 (ind. May 2027) | – | – | – | – | – | – | – | 47,000 | – |
| Swiss Myanmar tranche 3 (§3.3: 30 Jun 2027) | – | – | – | – | – | – | – | – | 24,947 |
| Closing cash | (6,101) | 13,202 | (21,230) | 269,219 | 234,722 | 200,225 | 162,728 | 175,230 | 168,180 |

Scenarios — month-end closing cash (USD)

| Scenario | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A. Central | (6,101) | 13,202 | (21,230) | 269,219 | 234,722 | 200,225 | 162,728 | 175,230 | 168,180 |
| B. Freeze (committed only) | (1,101) | 23,202 | (6,230) | 289,219 | 259,722 | 230,225 | 197,728 | 215,230 | 213,180 |
| C. Q3 run-rate continues | (11,737) | 1,930 | (38,138) | 246,675 | 206,542 | 166,409 | 123,276 | 130,142 | 117,456 |
| D. Central, FCDO claim slips to Jan 27 | (6,101) | (39,598) | (74,030) | 269,219 | 234,722 | 200,225 | 162,728 | 175,230 | 168,180 |
| E. Central + OSF released early Dec 26 | (6,101) | 13,202 | 278,770 | 269,219 | 234,722 | 200,225 | 162,728 | 175,230 | 168,180 |
| F. Central + Swiss T2 pulled to Dec 26 | (6,101) | 13,202 | 3,717 | 269,219 | 234,722 | 200,225 | 162,728 | 175,230 | 168,180 |

A: USD 5,000/month programme and travel. B: committed costs only. C: Q3's average variable spend continues (USD 10,636/month). D: as A, but FCDO claim 1 slips to January. E: as A, with OSF paying in early December. F: as A, with Swiss Myanmar tranche 2 pulled into December.

Every scenario is short in October. This is the 28 October payment run; no scenario brings receipts in before it.

December is short unless one receipt moves earlier. Freeze + Swiss tranche 2 in December closes at about USD 18,717; OSF in December closes at about USD 278,770.

If the FCDO claim slips to January, the low point is USD (74,030) at end-December. That is why the standby bridge is sized at USD 75,000.

After January, cash recovers to about USD 269,219 and stays above three months of the floor through June 2027 in cases A and B. In case C it falls to about USD 117,456 by June, which is the warning for the 2027 budget.

4. The October pinch point

| Item | Date | USD |
| --- | --- | --- |
| Cash at 12 October (Wise USD 2,456 + EUR 28,872) | 12 Oct | 31,329 |
| Chair stipend Q3 — EUR 2,000 (awaiting approval) | due 15 Oct | (2,251) |
| Free Thought Ltd — GBP 700, speech support (awaiting approval) | due 15 Oct | (928) |
| Payment run: ED 14,200; Comms Advisor ~5,383; Programme Mgr 3,500; Finance Mgr 2,000; COLA GBP 1,400; Rohingya Mgr 1,500 (net of advance); comms support, IT, bank | 25 → 28 Oct | (29,497) |
| Position after the run, before any programme or travel spend | 28 Oct | (1,347) |

Options before 28 October, in order of preference: (1) re-state FCDO claim 1 in GBP from ledger actuals and submit it early, asking Stimson to pay on receipt (cl. 6.5 rules out advances, but claim 1 covers costs already incurred); (2) defer the two non-staff bills (about USD 3,180) to November; (3) if still short, the board agrees which roster payment is delayed and for how long. Any deferral of the ED's fee is a related-party matter for the board, and Legal should advise first.

Correction to the 12 October dashboard note (CAP-520): that note put end-October cash at about USD 5,100. It left out the Communications Advisor's monthly invoice (about USD 5,383), which is raised by hand and not from a template, and Communication Support (about USD 649). The correct figure is shown above.

5. Change since the August cash plan

The August cash ceiling (CAP-389, 18 August) projected September USD 50,800, October USD 21,650, November USD 29,700 and December USD 550.

| Month-end | August plan | Now (freeze case B) | Change | Why |
| --- | --- | --- | --- | --- |
| Sep 2026 | 50,800 | 33,679 | (17,121) | Aug closed USD 3,837 below plan. Sep net cash decline was USD 42,433 against a USD 29,150 ceiling: Tavy Cussinel F-2026-002 GBP 4,000 (USD 5,303), New York accommodation USD 4,759 and Pennyhill Park balance GBP 1,888 (USD 2,525); other lines net USD 696 over |
| Oct 2026 | 21,650 | (1,101) | (22,751) | Sep shortfall carried forward (USD 17,121); Oct bills not in the plan (Chair stipend, Free Thought, SK Das Sep fee paid 1 Oct) USD 5,283; floor USD 347 above ceiling |
| Nov 2026 | 29,700 | 23,202 | (6,498) | October shortfall carried forward (USD 22,751), partly offset by a larger FCDO claim (+USD 15,600): about USD 52,800, not USD 37,200, because Schedule 2's first period runs June–October, not June–September |
| Dec 2026 | 550 | (6,230) | (6,780) | November shortfall carried forward (USD 6,498); December floor USD 282 above the ceiling |

6. Assumptions

| Area | Assumption | Source |
| --- | --- | --- |
| Opening cash | USD 33,679.30 at 30 Sep 2026 | Xero Balance Sheet `052baafa` |
| Roster | ED USD 14,200; Programme Mgr 3,500; Rohingya Mgr 2,500 (cash 1,500 until the advance clears in Dec); COLA GBP 1,400; SK Das 2,000 in Oct, 1,000 from Nov | Xero repeating templates; CAP-485 fee decision (effective date to confirm) |
| Communications | Advisor USD 5,383/month and Support USD 649/month (Q3 averages); the Advisor's invoice is raised by hand | Xero P&L Q3 |
| Overheads | IT USD 353, bank USD 56 per month (Q3 averages) | Xero P&L Q3 |
| Programme & travel | Central USD 5,000/month; Freeze nil; Q3 run-rate USD 10,636/month | Q3 spend above the committed floor |
| FCDO Phase II | Claim 1 (Jun–Oct) about USD 52,800 in late Nov; claim 2 (Nov–Mar) about USD 47,000 in May 2027; both within the £80,884.70 ceiling | Sub-grant Sched. 2; ledger USD 43,847.67 to 30 Sep + Oct roster share |
| OSF #4 | USD 300,000 on about 22 Jan 2027 (the 2026 tranche landed 22 Jan) | Award letter p.1 |
| Swiss Myanmar | USD 24,946.67 on 31 Jan 2027; USD 24,946.66 on 30 Jun 2027 | Partnership Agreement §3.3 |
| Rohingya Manager | Template and Swiss Myanmar term end May 2027; no cost from June 2027 | §17; Xero template |
| Audit | 2026 audit about USD 3,000, paid April 2027 | Deferred per ED, May 2026 |
| Excluded | Any new grant, the Q4 Chair stipend (paid in arrears, Jan 2027), FX movements, interest | Prudence |
| FX | GBP/USD 1.3258; EUR/USD 1.1255 | Xero rates on late-Sep / early-Oct transactions |

Proposed year-end accrual (draft, for auditor agreement)

Assets increase with a debit; income increases with a credit. FCDO Phase II and Swiss Myanmar costs incurred in 2026 have earned the grant income, but it is invoiced in 2027, so we recognise an accrued-income asset and the matching restricted income:

Dr  Accrued income — grants (current asset)            USD 33,614.00
      Cr  Grant income — FCDO Phase II (restricted)        USD 17,260.00
      Cr  Grant income — Swiss Myanmar (restricted)        USD 16,354.00

Debits USD 33,614.00 = credits USD 33,614.00. The entry is balanced. This would be a draft manual journal at 31 December 2026 and is reversed when the invoices are raised.