Board action register

hūmānus  ·  Q2 2026

Source

Q1 2026 Advisory Board minutes (13 February 2026)

Cut-off

29 May 2026

Open and recently-closed actions

| # | Action | Owner | Status |
| --- | --- | --- | --- |
| 1 | Approach Shafi to propose a mini project and budget for the Bangladesh camps (planning / execution / database test). | Eva | Open |
| 2 | Meet Somalia partners regarding wind-down of the Somalia programme. | Eva | Likely closed — annual report references AFRICOM determinations received 2025; needs confirmation. |
| 3 | Formal approval of 2024 audited financials per Dutch statutory process. | Eva / Board | Open — proposed to fold into agenda item 2 (Chair's context). |
| 4 | Add cash-flow statement, current cash snapshot and 12-month rolling cash flow to board packs. | Eva | Closed — Stacy's workbook and grants dashboard now standing. |
| 5 | Provide org chart with team locations, roles and contractual status as a standing item. | Ross / Eva | Open — to confirm with Eva for the Q3 pack. |
| 6 | Communicate Chair shortlist to recruiter; arrange interviews. | Eva | Closed |
| 7 | Notify Beena ahead of Chair interviews. | Eva | Closed |
| 8 | Ross to review finalist Chair candidates and contribute to second-round interviews. | Ross | Closed |
| 9 | Onboard new Chair / Dutch statutory director. | Eva | Closed (Els onboarded; AoA amendment workstream open). |
| 10 | Include Shafi in next team retreat where logistics permit. | Eva | Carry to next retreat planning |