2026 year-to-date spend vs budget — grant level

hūmānus  ·  Q2 2026

Source

Stacy's grants dashboard, 21 May 2026 cut (finance-docs/dashboards/grants_for_board.html)

Calendar progress

39% of 2026 elapsed at date of cut

Spend by grant

| Grant | Contracted (USD) | Received to date | Lifetime spend | 2026 YTD vs 2026 allocation | Status |
| --- | --- | --- | --- | --- | --- |
| OSF #4 (Jan 25 – Dec 29) | 1,500,000 | 600,024 | 317,654 (21.2%) | 65,932 vs 286,635 = 23% | On track; building carryover. |
| Stimson Swiss (Dec 25 – Jun 27) | 74,840 | 0 (Y1 tranche due 30 Jun 26) | 4,260 (5.7%) | n/a — project ramps Q3 | Risk of underspend (timing). |
| FCDO Phase II (Jun 26 – Mar 27) | 107,761 (working) | 0 | 0 | n/a — sub-grant unsigned | Largest 2026 cash-flow risk. |
| FCDO Phase I (Nov 25 – Mar 26) | ~58,000 | 57,005 | 60,994 | n/a — closed Mar 2026 | Closed; small overspend absorbed. |
| SDC Swiss Dhaka (Nov 24 – Apr 26) | CHF 182,788 cap | USD 193,538 (CHF 160,000) | — | n/a — close-out in progress | Final reports 30 Jun; final tranche ≤ CHF 22,788. |