2026 Budget Variance Report (YTD 25 May 2026)

P-06e  ·  Prepared by Stacy McGill (Finance Manager)  ·  As-of 26 May 2026  ·  Currency: USD unless stated

Headline

YTD spend USD 228,745 on an annual budget of USD 488,450 = 47% consumed at 40% of the year elapsed — running ~9 points ahead of straight-line pace on aggregate. The over-pace is driven by unbudgeted Operating Expense lines (General Expenses, Branding & Communications, Confidence Building Measures) rather than core programme run-rate.

Variance by donor (funding source)

Annualised YTD spend, by 2026 budget column.

| Donor / source | 2026 Budget | YTD spend (annualised) | Variance vs budget | Commentary |
| --- | --- | --- | --- | --- |
| OSF #4 (unrestricted) | USD 286,635 | USD 168,725 (annualised; YTD ~$66k) | (41%) underspent | Healthy headroom; ~USD 62k headroom before SDC re-tag (CAP-158) |
| Swiss Dhaka (SDC) | USD 35,560 | USD ~269k (YTD ~$105k; coding error — see flag) | +658% | Over-coded to SDC tracking; re-tag pass scheduled before §3.1 30 Jun 2026 final report |
| Swiss Myanmar (Stimson) | USD 48,312 | USD 10,883 (annualised; YTD ~$4.3k) | (78%) underspent | Underspent — first tranche due 30 Jun 2026 will bring spend forward |
| FCDO Phase I (closed) | USD 42,519 | USD 135,029 (annualised; YTD ~$53k) | +218% | Includes unbudgeted Confidence Building Measures $14,598; Phase I closed Mar 2026 |
| FCDO Phase II (unsigned) | USD 75,424 | USD 0 | (100%) | No grant agreement signed; budget worksheet only |

Variance by line item (top 10 movers, USD)

| Line | Annual budget | YTD pace budget | YTD actual | Variance | Variance % |
| --- | --- | --- | --- | --- | --- |
| Board Meetings | USD 4,000 | USD 1,600 | USD 8,936 | USD +7,337 | +459% |
| Audit Fees | USD 3,000 | USD 1,200 | USD 3,651 | USD +2,451 | +204% |
| Volunteer Stipends | USD 12,000 | USD 4,800 | USD 12,066 | USD +7,266 | +151% |
| Vehicle Hire & Sundry | USD 6,000 | USD 2,400 | USD 0 | USD -2,400 | -100% |
| IT & Software Expenses | USD 5,000 | USD 2,000 | USD 3,517 | USD +1,517 | +76% |
| Legal Fees | USD 12,000 | USD 4,800 | USD 1,359 | USD -3,441 | -72% |
| Partner Grants | USD 30,000 | USD 11,999 | USD 6,000 | USD -5,999 | -50% |
| Communication Advisor | USD 64,800 | USD 25,918 | USD 12,987 | USD -12,932 | -50% |
| Travel Expenses (Accommodation/Flights/Transport/Per diem) | USD 25,000 | USD 9,999 | USD 14,180 | USD +4,181 | +42% |
| Rohingya Manager | USD 31,250 | USD 12,499 | USD 10,000 | USD -2,499 | -20% |

Unbudgeted lines (not in original 2026 plan)

| Line | YTD actual | Commentary |
| --- | --- | --- |
| General Expenses | USD 29,194 | Largely sitting on SDC tracking — possible coding error; investigate before SDC final report |
| Branding & Communications | USD 9,807 | Rebrand pulse VAI → hūmānus; one-off but to be reclassified or rebudgeted |
| Confidence Building Measures | USD 14,598 | Q1 programme activity not separately budgeted; eligible against FCDO Phase I |
| Foreign Currency Gains and Losses | USD 215 | Wise revaluations on EUR/GBP wallets; immaterial |
| Total unbudgeted YTD | USD 53,813 |  |

Drivers & commentary

Expense side is broadly on plan after stripping one-offs.

Core programme staff (ED + Programme Manager + Communication Advisor) is running on contract; quarterly burn ~USD 45k/month is consistent with the annual budget once unbudgeted Q1 lines are recognised as one-offs.

Income side carries the structural risk.

USD 75,424 of 2026 budgeted spend is funded by FCDO Phase II, which is not yet signed. SDC restricted is over-coded and will absorb unrestricted reserves unless re-tagged.

Restricted / unrestricted segregation needs a re-tag pass.

SDC YTD-tagged spend (~USD 105k) far exceeds the contract residual (max CHF 22,788.10 ≈ USD 25k). The Finance Manager will run a re-coding pass before the SDC §3.1 final report (due 30 Jun 2026) — material amounts will move back to OSF #4 (unrestricted) tracking.

Closed projects with outstanding obligations.

SDC and FCDO Phase I are closed (per portfolio.md, last updated 2026-05-01) but both carry residual receivables and reporting deadlines. Stimson INV-0007 (FCDO I, USD 57,005) cleared 12 May 2026.

Recommended actions

·  Finance Manager — complete SDC tracking re-tag pass before 15 Jun 2026.

Required for SDC §3.1 final financial report (due 30 Jun 2026).

·  ED — confirm FCDO Phase II signature window with Stimson by 31 Jul 2026.

Drives whether downside cashflow scenario triggers (see P-06d).

·  Board — note recommendation to rebudget at H1 close.

Move unbudgeted Branding & General Expense lines into a formal mid-year plan; decide whether to fund from OSF carryover or programme reclassification.

Assumptions & data sources

·  YTD P&L 1 Jan – 25 May 2026 — Xero report ID b1fc6fb0-af72-4308-99f6-f34b08bc6206, pulled 26 May 2026.

·  Annual budget per finance-docs/budgets/2026 Budget-2.xlsx (Sheet1), total USD 488,450.

·  Donor-tracked YTD spend annualised from CAP-157 Xero P&L by Donors tracking option (21 May 2026 pull); refresh by close of Q2.

·  Months elapsed: 4.80 (1 Jan – 25 May 2026 ÷ 30.42).