# Strengthening Justice Pathways for Detained Rohingya Refugees in India

Partner Organizations:
hūmānus

The Azadi Project

Local community partners in Jammu, Delhi, Hyderabad, Assam, Haryana, and West Bengal

# Project Rationale and Context

It is estimated there could be up to 40,000 Rohingya living in India. India is not a signatory to the Refugee Convention, and as such Rohingya fleeing violence and persecution in Myanmar have no recognised status in India. In recent years, India has witnessed escalating arbitrary detentions and deportations of Rohingya refugees, including pregnant women, children, and the elderly. Under the current legislative framework, all Rohingya As recorded during the first phase of the project at least 150 cases of detention and over 120 deportations were logged across six Indian states between January and May 2025. Community researchers have gathered data despite security risks, revealing systemic violations of due process, prolonged incarcerations, and family separations.

Building upon this foundation, the next three-year proposal formalises a structured, rights-based approach to document, litigate, and report on cases of Rohingya detentions in India.

# Project Goal

To strengthen access to justice and legal protection for Rohingya refugees in India through evidence-based advocacy, strategic litigation, and community-driven documentation.

Use lessons learned to support expansion of litigation to include those affected by the National Registry for Citizens.

# Three-Phase Project Framework

## Year 1: Building the Detention Database through Community Data Collection

Objectives

- Build the Database

  - Train and deploy 15–20 Rohingya community data collectors in key detention regions.

  - Expand the database initiated under Phase I to include at least 300 verified cases of detention and deportation.

- Litigate Existing cases

  - Commence bail applications for 50 applicants

Activities:

- Conduct regional trainings (Delhi, Hyderabad, Assam) on secure data collection, digital safety, and trauma-informed interviewing.

- Provide stipends, smartphones, and encrypted data tools to community field researchers.
Strengthen mental health and gender-based violence awareness components through community workshops.

Outcome
A comprehensive digital database of detention cases accessible to partners for litigation and advocacy.
Strengthened network of Rohingya community documenters trained in ethical human rights research.

## Year 2: Strategic Litigation and Bail Applications

Objectives:
Initiate targeted legal interventions on behalf of detained Rohingya individuals and families.
Build legal precedents addressing arbitrary detention, denial of refugee rights, and unlawful deportation.
Collaborate with pro bono lawyers and rights organizations to support bail applications and case follow-ups.

Activities:
Commence exploratory work on individuals detained by NRC
File and monitor bail applications across high-priority jurisdictions.
Develop litigation toolkits and training manuals for partner lawyers.
Conduct paralegal training for HRLs to assist families in detention follow-up.

Outcome:
Minimum 25 successful bail releases during the implementation period.
Legal briefs and case summaries highlighting systemic gaps and violations.
Strengthened coordination between refugee communities and legal advocates.

Year 3: Reporting, Learning, and Advocacy

Objectives:
Synthesize learnings from documentation and litigation to produce evidence-based policy recommendations.
Publish and disseminate an annual Justice for the Stateless report.
Conduct advocacy engagements with media, international agencies, and human rights institutions.

Activities:
Hold annual stakeholder roundtables in Delhi and Geneva.
Develop multi-media reporting (videos, infographics, and digital stories) led by refugee researchers.
Conduct evaluation sessions with community teams to reflect on challenges and refine advocacy tools.

Outputs:
Final report documenting lessons learned, best practices, and policy gaps.
Public engagement campaign amplifying refugee voices.
Integration of findings into regional refugee protection networks.

## 4. Monitoring and Evaluation

Quarterly progress tracking by program managers and external evaluator. Use of standardized tools (qualitative interviews, case tracking dashboards). Annual review and adaptation cycle for methodology and partnerships.

## 5. 6. Sustainability and Exit Strategy

The project embeds sustainability through:
Capacity-building of community researchers and paralegals.
Strengthened legal networks advocating for refugee rights.
Open-access database and advocacy resources for future use by local partners.

## 7. Risk Management

Risks include political hostility, state surveillance, and security threats for field staff. Mitigation includes:
Secure data storage and encrypted communications.
Collaboration with recognized human rights defenders for protection mechanisms.
Adaptive data collection through virtual methods in high-risk regions.